Project Identification Form (PIF)

Project Type:

Type of Trust Fund:

- PART I: Project Identification

| Project Title: | Strengthening climate information and early warning systems in Zambia to support climate resilient development |  |  |
| --- | --- | --- | --- |
| Country(ies): | Zambia | GEF Project ID: |  |
| GEF Agency(ies): | UNDP | GEF Agency Project ID: | 5091 |
| Other Executing Partner(s): |  | Submission Date: | May 8, 2012 |
| GEF Focal Area (s): | Climate Change Adaptation | Project Duration (months): | 36 months |
| Name of parent programme: For SFM/REDD+ |  | Agency Fee ($): | 400,000 |

- Focal Area  strategy Framework:

| ### Focal Area Objectives | ### Expected FA Outcomes | ### Expected FA Outputs | ### Trust Fund | ### Indicative grant amount ($) | ### Indicative co-financing ($) |
| --- | --- | --- | --- | --- | --- |
| CCA-2 Increase adaptive capacity to respond to the impacts of climate change, including variability, at local, national, regional and global level | Outcome 2.2 Strengthened adaptive capacity to reduce risks to climate-induced economic losses | Output 2.2.1 Adaptive capacity of national early warning networks strengthened to rapidly respond to extreme weather events | LDCF | 960,000 | 4,300,000 |
| CCA-3 Promote transfer and adoption of adaptation technology | Outcome 3.1 Successful demonstration, deployment, and transfer of relevant adaptation technology in targeted areas | Output 3.1.1: Relevant adaptation technology transferred to targeted groups Output 3.2.1: Skills increased for relevant individuals in transfer of adaptation technology | LDCF | 2,850,000 | 18,302,478 |
| Sub-total |  |  |  | 3,810,000 | 22,602,478 |
| Project management cost |  |  |  | 190,000 | 1,107,522 |
| Total project cost |  |  |  | 4,000,000 | 23,710,000 |

- Project Framework

| Project Objective: To strengthen the climate monitoring capabilities, early warning systems and available information for responding to climate shocks and planning adaptation to climate change in Zambia. |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| - Project Component | - Grant type | Expected Outcomes | - Expected Outputs | - Trust Fund | - Indicative Grant Amount ($) | Indicative co-financing ($) |
| Transfer of technologies for climate and environmental monitoring infrastructure | INV | 1. Enhanced capacity of national hydro-meteorological (NHMS) and environmental institutions to monitor extreme weather and climate change. | - 1.1 Procurement and installation or rehabilitation (in case of existing) of 10+ hydrological monitoring stations with telemetry, archiving and data processing facilities. - 1.2 Procurement and installation or rehabilitation of approximately 40 meteorological monitoring stations with telemetry, archiving and data processing facilities. 1.3 Procurement and installation or rehabilitation of radar for monitoring severe weather. 1.4 Procurement and installation or rehabilitation of upper air monitoring stations. - 1.5 Procurement and installation or rehabilitation of satellite monitoring equipment to receive real time climate and environmental information. | LDCF | 2,660,000 | 8,400,000 |
|  | TA |  | - 1.6 Training of at least 3-5 officers to maintain and repair equipment, computer infrastructure and telecommunications (approx. $100,000). |  |  |  |
| - Climate information integrated into development plans and early warning systems | TA | 2. Efficient and effective use of hydro-meteorological and environmental information for making early warnings and long-term development plans. | 2.1 NHMS capacity to make and use climate forecasts (on daily to seasonal, as well as medium- to long-term timescales) is strengthened by training at least 4 forecasters. (approx. $100,000) | LDCF | 870,000 | 10,882,478 |
|  | INV |  | 2.2 Tailored sector-specific early warning products that link climate, environmental and socio-economic information on a range of timescales are developed, based on identified user needs. |  |  |  |
|  | INV |  | 2.3 National capacity for assimilating forecasts and monitoring into existing development planning, PRSPs and disaster management systems is built. |  |  |  |
|  | INV |  | - 2.4 Communication channels and procedures for issuing warnings (through both governmental and non-governmental agencies) are enabled (e.g. radio, newspapers, mobile phones, television etc). |  |  |  |
|  | TA |  | 2.5 Plan for sustainable financing for the operation and maintenance of the installed EWS developed and implemented. (approx. $100,000) |  |  |  |
| - Technical assistance for establishing an integrated early warning system | TA | 3. All components of implemented EWS are able to function as an integrated system within and between countries | 3.1 Technical guidance and training delivered to all relevant country agencies on selection and identification of cost effective technologies, including climate monitoring equipment, tailoring of climate information and generation of technically robust warning messages. 3.2 Key stakeholders trained on installation of new equipment, warning products and systems in coordination with other ongoing initiatives, including supporting and strengthening EWS related activities (equipment purchases, telecommunications, computer systems, decision support tools) implemented through other initiatives. | LDCF | 290,000 | 3,320,000 |
| Sub-total |  |  |  |  | 3,810,000 | 22,602,478 |
| Project management cost |  |  |  |  | 190,000 | 1,107,522 |
| Total project costs |  |  |  |  | 4,000,000 | 23,710,000 |

- Indicative Co-financing for the project by source and by name if available, ($)

| Sources of Co-financing | Name of Co-financier | Type of Co-financing | Amount ($) |
| --- | --- | --- | --- |
| GEF Agency | Government of Zambia/Joint UN | Grant | 22,150,000 |
| Bilateral agency | Government of Finland | Grant | 1,560,000 |
| Total Co-financing |  |  | 23,710,000 |

- GEF Resources Requested by Agency, Focal Areas and Country

| GEF Agency | Type of Trust Fund | Focal area | Country name/Global | Project amount (a) | Agency Fee (b) | Total c=a+b |
| --- | --- | --- | --- | --- | --- | --- |
| UNDP | LDCF | CC | Zambia | 4,000,000 | 400,000 | 4,400,000 |
| Total GEF Resources |  |  |  | 4,000,000 | 400,000 | 4,400,000 |

- part ii: project JustiFication

- The proposed project responds to priorities and actions identified in the NAPA of Zambia which articulate the need for securing, transferring and installing critical technologies, as well as developing the necessary systems for climate change-related information to permeate into decision-making processes. The technologies required to achieve these aims will increase the capacity of the national early warning network to forewarn and rapidly respond to extreme climate events. The total amount of funding requested, as articulated in the Letter of Endorsement and not including PPG and agency fees is USD 4,000,000.

- The NAPA clearly identifies a priority project on Early Warning Systems (EWS) along with projects associated with Food security, Water resources and Terrestrial ecosystems. The EWS project is not associated with any one particular sector and is expected to be relevant to multiple sectors, including the food/agriculture, water management, health and energy sectors.

A1.	Description of the consistency of the project with:

A.1.1  The GEF focal area strategies:

- This project is fully in line with LDCF/SCCF focal area objective 2 “Increase adaptive capacity to respond to the impacts of climate change, including variability, at local, national, regional and global level” and objective 3: Promote transfer and adoption of adaptation technology. It is specifically aligned with outcomes linked to these objectives including increased knowledge and understanding of climate variability and change-induced risks at country level and in targeted vulnerable areas, strengthened adaptive capacity to reduce risks to climate-induced economic losses, successful demonstration, deployment, and transfer of relevant adaptation technology in targeted areas and enhanced enabling environment to support adaptation related technology transfer.

A.1.2.  For projects funded from LDCF/SCCF:  the LDCF/SCCF eligibility criteria and priorities:

- Country ownership: The Government of Zambia has ratified the UNFCCC and is classified among the non-Annex 1 parties. These countries have also developed and submitted their National Adaptation Plans of Action (NAPA) and are entitled to benefit from the LDC Fund for the implementation of priority measures identified in their respective NAPAs. In implementing priority interventions identified in the NAPAs, the project is consistent with the Conference of Parties (COP-9) and also satisfies criteria outlined in UNFCCC Decision 7/CP.7 and GEF/C.28/18.

- The project focus is aligned with the scope of expected interventions as articulated in the LDCF programming paper and decision 5/CP.9. As climate impacts fall disproportionately on the poor, the project recognizes the links between adaptation and poverty reduction (GEF/C.28/18, 1(b), 29).

- Compliance with programme and LDC Fund policies: The project complies with the NAPA-identified urgent needs, all of which are relevant for supporting national development goals and for achieving MDGs 1, 3, 6 and 7.

- Financing: The project is designed to accommodate the additional adaptation costs of priority actions identified in the NAPAs and build on several other baseline projects and programmes. The co-funding for this project is also within the stated guidelines, with more than $5m in prospective co-funding. The relevance of the co-financing to the proposed LDCF project is outlined below and will be further elaborated on during the project preparation phase.

- Institutional Synergy and Coordination: The project outcomes will be primarily implemented through national implementation. The PIF therefore outlines project management costs that will be incurred by implementing partners at the national level (below 5%).

- The project is aligned with the framework of Poverty Reduction Strategy Papers (PRSP). In the case of Zambia, the relevant PRSP pillar is:

- Governance (improved security, including security from natural disaster) and Agriculture (technology development and food security efforts).

9.	The project outcomes are closely aligned and coordinated with efforts already underway within Zambia to promote development which is resilient to climate change at the national and local levels. The project is focused on strengthening the capacity of national and sub-national entities to monitor climate change, generate reliable hydro-meteorological information (including forecasts) and to be able to combine this information with other environmental and socio-economic data to improve evidence-based decision-making for early warning and adaptation responses as well as planning. The proposed project will be implemented at the country level by the lead Ministry mandated to advance climate monitoring including management of climate data in full collaboration with other relevant line Ministries who rely on the information for planning purposes (Disaster Management, Agriculture, Water, Finance and Planning etc). Sub national authorities (Provincial and/or District officers, Municipalities, civil society (women and youth associations, NGOs, media, farmers’ associations) and the private sector will all also be important stakeholders (as end users) and will be provided with the space and opportunity to contribute to the design of the project in each country. Details of the institutional coordination will be spelt out in the project document that is prepared during the PPG phase with the full participation of key stakeholders in each country including GEF OFP, UNFCCC FP, and other key senior Government officials including private sector and civil society representations as well as donor representatives.

- Monitoring and Evaluation: The implementation of the project’s activities will reflect UNDP-GEF monitoring and evaluation standards and procedures, in line with the requirements of the LDCF. Details for monitoring and evaluation will be articulated during the project development phase.

A.2. National strategies and plans or reports and assessments under relevant conventions, if applicable, i.e. NAPAS, NAPs, NBSAPs, national communications, TNAs, NIPs, PRSPs, NPFE, etc.:

- The link between this project strategy and the NAPA is centered on a common goal of informing climate resilient development planning and sector management through improved national systems that generate relevant climate information.

- Zambia’s NAPA identifies the provision of irrigation/water management, sustainable land management and the promotion of a stronger role of early warning systems for adaptation as the top priorities for facilitating better management of climate-related risks. Its Priority Action number 2 project, “Strengthening of early warning systems to improve services to preparedness and adaptation to climate change,” the following activities are featured:

- Development of infrastructure for early warning advanced planning purposes;

- Establishment of a National Climate Centre;

- Collection of the required climate, environmental and health data;

- Conducting field surveys in representative localities to identify climatic and non climatic disease risk factors;

- Establishment of an effective climate data management system;

- Development of Human capacity for regular monitoring of climate stations for data quality;

- Devising an effective information dissemination process to all sectors that may be affected by climate change.

- NAPA consultations also suggested that indigenous knowledge for climate forecasting could be further studied and integrated into a climate-based early warning system for disease outbreaks.

- B.  Project Overview:

B.1. Describe the baseline project and the problem that it seeks to address:

- Problem

- Many countries in Eastern & Southern (E&S) Africa suffer from low rates of development. In particular, Zambia is in the lowest 20% of countries worldwide, ranked by both Gross National Income (GNI per capita) and the 2011 United Nations Human Development Index. These countries are particularly vulnerable to climate-related shocks (either to the economy or to unprotected populations), which threaten to undo years of development assistance and asset accumulation, especially within poor populations. One way to help mitigate the impact of these climate-related shocks is to warn populations, businesses and governments in advance of an impending or likely damaging event through an Early Warning System (EWS).

- The fundamental problem in many countries such as Zambia is that a complete EWS, which generates knowledge of the risks (vulnerability & hazard), has capacity to monitor, analyze and forecast hazards, provides communication and dissemination of alerts and warnings, either does not exist or does not function as well as it ought to be relevant and useful for long-term planning, management and risk reduction activities. For many LDCs, this status unnecessarily imperils lives and assets. Reasons for this situation involve a lack of both hard and soft technologies and the capacity to utilise those technologies in an appropriate manner. This results in: i) a limited understanding of current and future risks; ii) limited monitoring and forecasting of climate-related hazards; iii) inappropriate communication and packaging of warnings; iv) restricted responses to impending disasters and v) constrained planning for slow-onset changes due to climate change that will require a transformational shift in economic development and risk reduction efforts. The infrastructure and technology on which to build these services is lacking. Without investing in the capacity to generate information, especially the monitoring and forecasting of climate-related hazards, the EWS will never function as optimally as it could. The aim of this proposal is to strengthen the EWS of Zambia, largely through improving national capabilities to generate and use climate information in the planning for and management of climate induced hazard risks. It will achieve this by implementing the transfer of appropriate technology, infrastructure and skills.

Changes in climate-related hazards and likely impacts

- Africa is the continent expected to suffer the most under anthropogenic induced climate change, both due to expected increases in climate hazards and its already high vulnerabilities to those hazards across a range of sectors. Zambia is classified as a Least Developed Country (LDC), which is recognized by the United Nations Framework Convention on Climate Change (UNFCCC) as among the most vulnerable to the impacts of climate change. These vulnerabilities span many sectors, livelihoods and assets within each country and the region in general.

- Water is a scarce resource in Zambia and it's availability both for agriculture and domestic consumption is impacted severely by drought, which has been and will continue to increase in intensity and frequency (due to both changes in rainfall and increasing temperatures), especially in sub-tropical and semi-arid regions. These hazardous events often lead to impacts on food security and health such as those seen recently in the horn of Africa. Flooding due to heavy rainfall over a short period of time has wreaked havoc in both urban and rural (river basins/watersheds) environments, with attendant impacts on health and the spread of disease e.g. recent floods in Mozambique/South Africa and across much of West Africa in 2009. Whilst the upswing in deaths attributed to floods in recent years may largely be due to population dynamics, many deaths can be avoided with sufficient early warning. These risks and associated losses are expected to increase in some regions due to the increased availability of atmospheric moisture and intensity of rainfall in the future.

- Severe weather, associated with convective weather, atmospheric heating and moisture, will likely increase in many regions and can result in increases in rain, hail and winds. Whilst changes in cyclone frequency are uncertain, most models and observations suggest an increase in cyclone intensity (or an increase in the frequency of more intense cyclones), therefore where cyclones are a current risk they are likely to be more of a risk in the future (including impacts through several hazards - rainfall, storm surge and winds). Sea level rise is a problem for many low lying coastal areas where large populations often assemble and the slow and steady rise of mean sea level results in more frequent flooding and coastal erosion. Rises in temperature which affects all countries and regions, results in an increase in the frequency of heat waves and extremely hot days/nights, which in turn affect the health of humans, ecosystems and urban environments.

- Changes in the above climate-related hazards will negatively affect a range of sectors. Of particular concern is the agricultural sector which is an important component of the economy and forms the basis of many rural livelihoods. Droughts, floods and increases in temperature reduce the ability to grow crops, as well as affecting other aspects of the value chain e.g. drying/storage and transport to market.

Underlying causes

- Whilst the EWS in many different countries serve different sectors or users, they also currently share common problems; i) insufficient meteorological and hydrological observing stations to monitor the current state of the climate and hydrology, map risks and detect long-term trends; ii) insufficient use of satellite data for monitoring different aspects of the environment and providing information in regions not covered by the meteorological and hydrological stations; iii) limited use of climate forecasts on daily to seasonal timescales and; iv) limited packaging of different sources of information to inform risk reduction efforts in different sectors; v) inappropriate communication of EWS messages and vi) lack of trained personnel to effectively run and maintain the different aspects of the EWS.

- A lack of meteorological and hydrological monitoring stations in Zambia has meant that many important regions and populations vulnerable to climate hazards are not monitored e.g. drought conditions (rainfall) are not monitored for important agricultural lands, intense rainfall is not monitored in areas prone to landslides and flooding, and rapid rises in rivers as a precursor to flooding goes unnoticed. Therefore many potentially threatening hazards are not forewarned because of a lack of monitoring stations. Where stations exist they are often manually operated and do not report measurements for days to weeks after the climate hazards have passed. Equipment failure is also common and regular checks and maintenance often neglected due to insufficient funds, incentives and regulatory policies resulting in poor quality and unreliable data for making management decisions related to climate change induced disaster risks.

- It is now common practice to utilize satellite imagery as a useful tool for monitoring areas where meteorological and hydrological monitoring stations do not exist and aspects of the environment useful for assessing current risks e.g. vegetation monitoring helps assess crop performance and images of floods help understand which areas are more at risk. Additionally satellite data may be used to predict rainfall or monitor severe weather. However, many developing countries do not utilize these technologies because they do not have the necessary equipment to access the data or do not have the human resources to use the data.

- The radar network for monitoring severe weather is limited in Zambia, often to airports where its main application is for air traffic control. This is largely a consequence of the high costs (for infrastructure, maintenance and human resources to run the equipment). Given most radar have a range of approximately 75-200 km covering large areas becomes very costly.

- Climate forecasts for the coming 1-7 days are produced using a combination of Numerical Weather Prediction (NWP) models and predictions either from neighboring countries or international centres. Seasonal forecasts are also produced using tools developed at international centres. In situations where forecasts are externally sourced, forecasters are dependent on the applicability of the forecasts to local conditions and restricted in their ability to apply local observations to develop better forecasts.

- Often forecasts and climate information is given in the same standard formats for different users and this restricts their interpretation and application. For example, agricultural extension officers require information about the start of the rains, or the frequency of days with rain, whereas those monitoring floods require information on rainfall intensity. Extracting these particular attributes from forecasts is currently not undertaken. This information is then more useful when packaged with other sources of data e.g. satellite maps showing current vegetation and rainfall, or soil moisture as an indication of flooding potential etc.

- Further problems are caused by a lack of trained personnel who are capable of maintaining an observational network, generating information for specific sectors, as well as interpreting the data in ways that non-technical stakeholders can understand. This human capacity is required to:

- Replace components of the observing networks when they fail;

- Manage and run any forecast models;

- Understand how users interpret data and design information packages that address these needs;

- Be able to combine, manipulate and overlay different data to identify areas at risk.

Long-term solution and barriers to achieving it:

- It is expected that as climate change unfolds the frequency and intensity of climate related shocks will change, therefore improving EWSs is one way to adapt to a changing climate. As an adaptive measure EWS also benefit the poorer segments of society, those who do not necessarily benefit from large protective infrastructure projects. Furthermore, improving the EWS also provides benefits for long term planning and helps NHMS and other institutions build capacity to service other needs e.g. for land-use and agricultural planning, hydro-electric power etc.

- To allow countries to better manage severe weather related disasters, food security and agricultural production, scarce and dwindling water resources and make their socioeconomic development process less vulnerable to climate-related risks it is essential to:

- enhance the capacity of hydro-meteorological services and networks for predicting climatic events and associated risks;

- develop a more effective, efficient and targeted delivery of climate information including early warnings;

- support improved and timely preparedness and response to forecast climate-related risks and vulnerabilities.

- These objectives require developing robust weather and climate observation, forecasting, and monitoring infrastructure, which can be rapidly deployed, is relatively easy to maintain, and simple to use. Such a weather and climate monitoring system can provide countries with the capacity to develop: (i) an early warning system for severe weather; (ii) real-time weather and hydrological monitoring; (iii) weather forecasting capabilities (Numerical Weather Prediction); (iv) agro-meteorological information and services (including integrated crop and pest management); (v) applications related to building and management of infrastructure; (vi) land, air and maritime transport management; (vii) integrated water resources management; (viii) coastal zone and land management; and (ix) planning and policy making processes.

- However, there are significant policy, institutional, financial, technological and informational barriers that prevent the desired situation from emerging. These barriers include:

Lack of weather and climate monitoring infrastructure

- In all countries considered here there has been a steady decline in infrastructure dedicated to monitoring the climate, hydrology, environment and severe weather (e.g. meteorological and hydrological observing stations, satellite receivers and weather radar) for the last 20-30 years. Whilst this situation has been ameliorated by specifically targeted project interventions, this has often benefitted a few countries or a particular aspect of the early warning system (e.g. African Monitoring of the Environment for Sustainable Development (AMESD) to improve use of satellite data or the “Weather for all” initiative to improve weather station coverage). Recently the need for a systematic improvement of the observing network is recognized by the Global Climate Observing System (GCOS) which in its reports to the UNFCCC notes that “Developing Countries have made only limited progress in filling gaps in their in situ observing networks, with some evidence of decline in some regions, and capacity building support remains small in relation to needs”. The installation of new infrastructure also requires several practical condiderations: i) safety of the equipment; ii) power sources; iii) long term durability; iv) access for maintenance and v) transmission and archiving of data.

Limited knowledge and capacity to effectively predict future climate events

- The scientific and technical capabilities required to effectively identify hazards and forecast their potential impacts on vulnerable communities are often weak. This may be due to a lack of either infrastructure (i.e. computational equipment), software (model code and associated routines) or human capacity/skills to programme and run the model code. Running forecast models is a highly skilled task and requires many years of education and training. Forecasters, with highly sought skills, are often lured into more lucrative work.

Inconsistent use of different information sources across and within country borders

- If there is not a clear legal mandate for the issuing of warnings then messages may be confused (between different sources) and not acted upon. There needs to be an official process for generating warnings that include communication between sectoral ministries and with communities where disasters are experienced. Representatives from different ministries convene, assess the situation and warning messages are conveyed. This allows a wide range of views and evidence to be considered (including information from international and regional sources), though the process needs to be clear and act efficiently if warnings are to be issued in time.

No systematic forecasting of climate hazards, risks and timely dissemination of warnings

- When climate information is available (monitoring and forecasts), it should be translated into specific hazards experienced by different sectors and users e.g. heat units for agriculture or wave heights for managing coastal shipping. Without translation into information that can be easily understood by users, the information is unlikely to be used. This information should then be combined with known vulnerabilities to identify areas and communities at risk. This is currently not part of the process for issuing warnings in most cases.

Lack of environmental databases for assessing the risks posed by climate variability and change

- Calculating risks for known vulnerabilities requires a comprehensive archive of information related to vulnerable communities, infrastructure, roads, shipping, access to markets, flood prone areas, cropping patterns etc. This information are held in disconnected databases or computers spread across different government departments and ministries. All the information required to assess vulnerability and calculate risks needs to be accessible, either through a central database/repository, or through distributed networks.

Long-term sustainability of observational infrastructure and technically skilled human resources

- The maintenance of monitoring equipment, the human capacity to use and repair this equipment, process data and develop early warning packages, all require constant income streams and annual budgets. These are needed beyond the lifetime of this project and therefore require suitable business models and financial mechanisms to be developed. The NHMS often struggles to pay for the maintenance and upgrade of existing equipment which is recognized as a limiting factor and various levels of public-private partnership have been suggested, including the use of an intermediary organisation. Regardless of the business structure it is clear that delivery of targeted services, such as those proposed here, are essential for generating products and revenue that both public and private clients will pay for. This revenue can then support the maintenance of the observational infrastructure and the salaries of skilled staff to use it and generate the early warning products.

Baseline Project(s) the project will build on:

- UNDP’s Africa Adaptation Programme (AAP), financed by the Government of Japan - is a multi-country programme working in a number of countries including Burkina Faso, Cameroon, the Republic of Congo, Ethiopia, Gabon, Ghana, Kenya, Lesotho, Malawi, Mauritius, Morocco, Mozambique, Namibia, Niger, Nigeria, Rwanda, Sao Tome and Principe, Senegal, Tanzania, Tunisia, and Zambia. Total funding for the programme is $91m. None of this financing has been considered as co-financing as the funds are for adaptation activities. However, it is mentioned here as this proposal seeks funds to build on activities financed by UNDP AAP.

- SADC Regional Meteorology Project (SAMPRO). Financing: $10.4m. SAMPRO is a regional development cooperation project based on an agreement between the Government of Finland and the Secretariat of the Southern Africa Development Community (SADC). An Inception Phase executed by the Finnish Meteorological Institute (FMI) in collaboration with the Meteorological Association of Southern Africa (MASA). The objective of the Inception Phase is build basis for multiyear regional project in Southern Africa and to strengthen the implementation of meteorology services in Southern Africa by building capacity and to make the function of early warning systems more effective. The purpose of cooperation in meteorology is based on the regional meteorology priorities set by the SADC ministers responsible for Transport and Meteorology. At present it is not clear how this investment will be distributed between countries and activities – for this PIF it is assumed that 15% is taken to be for Zambia-specific activities (details will be clarified during the PPG phase).

- The Government of Zambia/UNs Joint Programme on climate change and disaster risk reduction has the goal to reduce people’s vulnerability from the risk of climate change, natural and man-made disasters and environmental degradation by 2015. The value of this programme is $22.15m, and it includes a focus on strengthening EWSs, involving calculating climate variability trends, mapping vulnerability, developing a GIS system to hold the data and communicating messages, disaster simulations and preparing responses.

- The Danish Meteorological Institute (DMI) has established a twinning project with the Zambia Meteorological Department (ZMD) through the project Capacity development for climate change at the Zambia Meteorological Department. The goal is to enhance ZMD’s capability in the fields of climate variability and change in Zambia, including modelling, archiving, quality control and analysing historical data. The co-financing associated with this programme will be detailed during the PPG phase.

- The Zambia Meteorological Department, through its RANET Project, has in the last four years involved rural community members in collecting climate information. The project provided some 3050 community members in remote rural areas with rain gauges to take rainfall measurements and the systems has been used to both collect climate data and disseminate warning messages. The co-financing associated with this programme will be detailed during the PPG phase.

- Other projects and programmes outlined in the Minister of Finance’s budget speech offer further opportunities for co-finance that will be detailed during the PPG phase. In particular those initiatives associated with agriculture and rural development, extension services, storage for grains, rural infrastructure and health.

- B.2. Incremental/Additional cost reasoning: describe the incremental (GEF Trust Fund) and the associated Global environmental benefits to be delivered by the project:

- The first component of the proposed project seeks to establish a functional network of climate (meteorological and hydrological) monitoring stations and associated infrastructure (satellite and severe weather monitoring) as a basis for understanding climate change and building an early warning system to increase resilience to climate-related shocks. The second component concerns itself with developing connected systems and processes to enable the data from such a network to be translated, combined, reinterpreted and communicated to intended users. It will also develop the human capacity to make such a system work. The third component will coordinate activities with ongoing projects and regional activities to ensure best practices and maximise the effectiveness of implemented infrastructure and systems.

- Component 1: Transfer of technologies for climate and environmental monitoring infrastructure

- This component will procure and install infrastructure to improve access to climate and environmental information for a functioning EWS. Details of this procurement will vary depending on the required types of EWS (e.g. for floods, drought, severe weather etc.), existing infrastructure and telecommunications, capacity to utilise the equipment and associated data. Additionally, during the PPG phase potential climate change hotspots (where both vulnerabilities and hazards are expected to be high) will be considered when deciding where to place infrastructure e.g. meteorological stations in vulnerable regions etc.

- Baseline Situation including Projects

- Zambia Meteorological Department (ZMD) maintains 37 full-time weather stations, which are supplemented by a network of voluntary stations (mainly rainfall stations) run by various organizations such as Department of Water Affairs, Zambia Electricity Supply Corporation (ZESCO), Government institutions, missions, schools, as well as individuals. Observations include rainfall, temperature, wind direction and speed, evaporation, sunshine duration, as well as visual observations (e.g. identification of clouds) are taken at prescribed times in accordance with WMO regulation. This station network is complimented by other data sources which include upper air ascents, and satellite receiving systems. In 2008, expenditures for EWS under national policy in Zambia were $780k.

- However, Zambia’s network of stations may be considered inadequate given the size of the country. Most stations are located at aerodromes/airports, despite the fact that much of Zambia is predominantly an agriculture-based economy. As of 2010 ZMD does not carry out upper air ascents, has no weather radars or lightning detection system, and has non-existent communication facilities with other countries/institutions.

- ZMD has teamed up with the Danish Meteorological Institute to implement the project, “Capacity Development for climate change at the Zambia Meteorological Department.” The project will improve the existing observation network and will upgrade systems to ensure good spatial coverage and a good selection of meteorological parameters. Data management and data analysis techniques will also be improved. Training is provided on numerical weather forecasts and details of this project (financing etc) will be provided on completion of the PPG phase

- Additional cost reasoning

- Under this component of the project the Government of Zambia will be able to use LDCF resources to procure, install and/or rehabilitate critical infrastructure required to build and/or strengthen the climate-related observational network. In all equipment purchases an assessment of existing equipment will be made, noting the manufacturer, whether it is still working and whether the NHMS has an interest in continuing with particular makes/models. This will need to be weighed against the costs of potentially cheaper solutions and the added costs of training personnel to service different products.

- Under Output 1.1 of the proposed project, LDCF resources will be used for the procurement and installation or rehabilitation (in case of existing) of 10+ hydrological monitoring stations with telemetry, archiving and data processing facilities, which will enable the NHMS to monitor river and lake levels. In turn this allows the NHMS to identify dangerous floods before they occur, issue warnings for dam/transport managers downstream and alert communities at risk. All stations will be fitted with appropriate means for relaying data to central servers (e.g. via GPRS or satellite telemetry).

- Under Output 1.2, LDCF resources will be used for the Procurement and installation or rehabilitation of approximately 40 meteorological monitoring stations, also with telemetry, archiving and data processing facilities. Comparison of the network coverage with the risk and vulnerability maps, calculated or sourced during the PPG phase, will be used to identify underserved locations where data from additional stations will be most useful. As early warning and up to date monitoring is a priority, Automatic Weather Stations (AWS) using GPRS mobile telecommunications will be prioritised and where this is not available the feasibility of using more costly satellite communications will be assessed (including implications for budgets and future running costs). Coordination with the PPCR funded activities to improve mobile telecoms coverage will be beneficial. In cases where stations have been neglected but the site (fences, towers etc.) are still functional, LDCF resources will be used to replace existing sensors and data loggers as historical observations from the site can be used with newly acquired data to create longer timeseries for detecting climate changes. Preliminary estimates of costs for purchasing needed additional weather stations (based on government estimates) are $1m for 40 stations.

- Under Output 1.3, LDCF resources will be used to procure equipment for monitoring severe weather. Radar equipment for doing this is costly (purchasing and maintaining the equipment, as well as training and paying personnel to operate it) and budgets will only allow for the purchase of 1-2 such items. Depending on the type of radar and function the useful range is of the order 75-200 km. This limits the practical use of this equipment for specific locations with either a high vulnerability to extreme weather (e.g. large urban or coastal areas prone to flooding), or high values services/assets such as airports. Alternative options using different technology to achieve similar results will be investigated and assessed, depending on the application e.g. combining satellite and in-situ observations, and lightning detection as a proxy for extreme weather.

- Upper air monitoring stations, through either radiosonde ascents or other remote sensing technologies, are useful for improving regional numerical weather predictions and global climate models run by international forecasting centres. There were no baseline activities identified with this activity, besides regular procedures implemented by the NHMS. Through Output 1.4 LDCF funds will be used to procure the equipment needed to make upper air soundings. The exact number of installed upper air stations will be decided as part of the PPG phase given other equipment needs. None of the ongoing baseline projects suggest that new upper air stations are being implemented.

- LDCF resources will be used for the procurement of satellite receiving equipment and establishment of data/image processing facilities (Output 1.5). This output will build on the AMESD and recently launched SERVIR programmes at the regional level, as well as Zambia’s current installation of satellite reception equipment. The potential uses of satellite data and imagery for planning and management purposes in the context of food security, and water management will be established based on country specific contexts, users of information, needs (in the short-term disaster management, medium-long term planning) etc. This will involve coordination with other projects such as FEWSNET etc. If online data is not available in time to support required decisions then satellite receiving equipment will be purchased and systems established to provide the required information.

- Under Output 1.6, LDCF resources will be used to develop the human technical capacity required to maintain and use the equipment made available through the LDCF. Personnel responsible for the running of the equipment and receiving/archiving the data that it produces (including manually operated stations where necessary) will be trained, along with back up personnel and replacements. This includes ensuring that there is an incentive mechanism in place to sustain the system that is set up with the LDCF resources. No baseline activities were identified with this output besides routine NHMS activities.

- Table 1: Summary of needs that are relevant to Component 1 (to be developed in detail during the PPG phase):

- Zambia

- Automatic Weather Stations (purchasing, installation). Rehabilitate existing stations

- Upper Air Stations (purchasing and installation)

- Forecasting and Visualization Tools

- Weather radar, weather prediction models

- Upgrade satellite receiving equipment and electronic links

- Component 2: Climate information integrated into development plans and early warning systems

- Much of the value of early warnings (whether a user changes their actions or lives/assets are safeguarded) is dependent on the packaging, communication and dissemination of those warnings. The effectiveness of warnings can be improved either through improving the forecasts/monitoring information, communications or the decision-making process. This component is primarily concerned with improving these aspects of the EWS. Specific details on the exact type of EWS information and risk management tools (for flood warnings, agricultural extension advisories, weather index insurance, transport planning etc) will be determined at the PPG phase and additional actions designed to meet those priority needs.

- Baseline Situation including Projects

- With funding and facilitation assistance from the UNDP CO in Zambia, the Government recently created its Climate Change Facilitation Unit, an interim body to strengthen national coordination of climate change response efforts. The PPCR also reports that Zambia requires improvements in the ability to monitor inundation, flash flooding/heavy rainfall and drought/dry periods, combining appropriate ICT technology to structure and geo-reference information, as well as ensuring that information is in simple language and can be understood by users. The Disaster Mitigation and Management Unit (DMMU) currently has the mandate to collect information from the departments of Meteorology and Water affairs and issue warnings based on this information. DMMU is also supported by the joint-UN programme on reducing vulnerability to climate change to conduct an evidence-based response to climate change and develop effective national, sectoral and local early warning systems.

- Additional cost reasoning

- The capacity to make and use daily to seasonal climate forecasts will be developed through Output 2.1. This will link to ongoing activities at the NHMS and will ensure the capacity to run numerical weather prediction models, or be able to usefully generate and use data from these models run elsewhere with the region or at international centres. The data from these models should be linked to tailored products developed in output 2.2 and the decision processes in output 2.3. Numerical weather prediction is being undertaken and the gaps between existing forecasts systems and those required for climate resilient planning purposes will be evaluated during the PPG phase, including use of indigenous knowledge when useful (see CC DARE projectError: Reference source not found). Data sharing with regional NHMSs will be encouraged as this helps develop forecast products and the observations from other countries, collected through output 1.2, help understand the errors in the forecast models.

- Output 2.2 will develop new tailored products to serve the information requirements of users in different sectors and locations. These products will be developed through consultations with the intended users of the information and appropriate research organizations. Information and data from the monitoring infrastructure (weather and hydrological stations, radar, and satellite monitoring) will be combined to produce new user-relevant information. As an example, satellite and weather station observations can be combined to derive a spatially continuous dataset and estimate rainfall for locations which have no meteorological stations. Using these data the water balance of crops can be estimated for wider regions and these can be used as part of agricultural advisories. Improved availability of data to generate these products will also be implemented e.g. where important climate records reside in paper format, they will be digitised and used to better describe local microclimates, hence improving the baseline hazard mapping. It is currently not clear which projects are currently undertaking this work and this will be determined during the PPG phase.

- Assimilating the forecasts from output 2.1 and tailored products from output 2.2 into existing EWS activities and processes will be the aim of Output 2.3. This will involve assessing the information needs of different decision-making processes e.g. for flood warnings, drought warnings, food security, water management etc and designing a set of information products that will inform the process. Existing EWS for particular sectors (e.g. drought and floods) can be used to extend knowledge and skills to other sectors which need similar EWS and experience. Climate monitoring information from component 1 and forecasts from output 2.1 will be combined to identify regions where risks are currently high and likely to get worse. Where necessary satellite imagery will be used to assess the current extent of climate-related hazards and this information will be combined with agricultural (crop), flood risk or other sectoral models to help the decision making process. Training on the use of these technologies will be provided where needed. Several baseline projects are currently undertaking these activities, including UNDP, WFP and PPCR. Coordination for this output will therefore be important.

- Output 2.4 will establish communication strategies and processes targeted to each identified sector and user. The aim is to effectively communicate early warnings, and advisory packages developed through Output 2.3, in the most useful way for different users/audiences. These strategies will vary between countries as communications technologies, language and cultural norms vary. Using software and technology in innovative ways will be explored e.g. Google earth for presenting forecasts and identified risks. Lessons and experiences in other parts of Africa will be assessed for their potential to upscale e.g. using innovative techniques to communicate agrometeorological advisories. This will build on the work undertaken by UNDP, WFP and PPCR, with the potential to extend lessons learnt to other countries.

- Output 2.5 will assess the sustainability of the EWS, taking cognizance of the current funding mechanisms and allocated budgets. It will assess where funding shortfalls are most acute and where budgets are likely to be reduced in the future. A comprehensive needs assessment for climate services will be carried out (how needs are currently met, opportunities for private partnerships and gaps in the current services), as well as the willingness and ability to pay for such services across a range of stakeholders, both private and public. Where suitable legal arrangements exist and where governments are willing, private companies will be approached to test their willingness to engage in a public-private partnership with the NHMS or associated entity. Similar activities within the country or region will be approached to learn from their experiences (e.g. the Weather Information for Development (WIND) initiative in Kenya). No baseline projects were identified with this output at this stage.

- Table 2: Summary of needs that are relevant to Component 2 which will be developed further during the PPG phase:

- Zambia

- Apply appropriate ICT technology for communication with communities

- Access to satellite imagery and integration into development of EWS messages

- Formulate coherent policy for disseminating climate information

- Flood warnings, agricultural advisories, drought monitoring

- Component 3: Technical assistance for establishing an integrated early warning system

- This component will provide overall technical assistance to the project to help implement the most cost effective solutions given budgetary, human and technical restrictions. It will provide scientific support to ensure that climate and environmental information is utilized in line with accepted norms as well as coordination with other in-country and regional development partners undertaking similar work. The benefits of other EWS activities will be promoted by sharing best practices, support tools, experience and information between countries, sectors and agencies.

- Baseline Situation including Projects

- Zambia lacks the technical capacity to design and implement cost-effective systems which incorporate climate monitoring, forecasting and other environmental information (e.g. from satellites) into processes to inform preparedness and response activities. The skills often exist to implement parts of the processe (e.g. WFP in Zambia has been designing a GIS-based early warning system for food security), but linking these into a wider framework requires dedicated resources. Furthermore, the utility of climate monitoring and forecast information is limited by the use of standard meteorological formats e.g. seasonal mean rainfall, which is difficult to relate to agricultural impacts or floods. Developing and testing new products based on available data, skills and resources can improve the use and interpretation of EWS messages.

- Presently there is ad-hoc coordination between countries on EWS-related activities and within countries the implementation of EWS is usually tied to the availability of project funds, which may be earmarked for particular activities, equipment or service providers. This can result in breaks in the flow of information, inability to utilize technologies or the absence of important information. Several development organisations are, however, working to overcome these limitations, both at the regional level (Clim-dev, SADC-HYCOS, GCOS and AMESD – see coordination projects) and across many countries simultaneously (the Finnish SAMPRO project, GFDRR, PPCR and UNDP projects). It is important that any new initiative such as this one coordinates with these activities as no one initiative can provide all the requirements of a fully functional EWS.

- There are examples of best practices being shared e.g. the regional climate outlook forums (SARCOF) where climate scientists come together from each country to make a consensus forecast using similar tools and methods. However, regional coordination is often limited e.g. neighbouring countries often use a different weather prediction model, though they are predicting for the same areas. Combining the forecasts from these different sources can provide better forecasts. Similarly, weather radar may overlap an adjoining country and could provide useful information for other countries. However, this sharing of information and the processes to enable it are often lacking

- Additional cost reasoning

- Output 3.1 will provide technical guidance and training on the selection of appropriate hardware/equipment, assessing it’s technical capabilities and cost effectiveness. This will be based on the intended purpose and accuracy of required data, the lifespan of the equipment, cost of maintenance (including specialised skills) and integration with existing systems. It will ensure that equipment can be maintained beyond the lifetime of the project. Further technical guidance will be provided on the appropriate uses of available data, how to use it to generate meaningful information which can either be used to generate a warning or combined with other sources of data (climate and environmental e.g. from satellites) to generate warnings. Appropriate technologies for this purpose will be suggested, with the emphasis on workable, low cost solutions when available. Baseline projects such as the SAMPRO and GCOS projects will be approached for their experiences, as well as the experiences of the NHMS in operating different infrastructure.

- Coordination with other ongoing activities led by AAP, PPCR, AMESD etc. will undertaken through Output 3.2. Where different sources of equipment and software are used they will be assessed for compatibility and ways in which they may be combined suggested to the respective governments. Where possible complimentary equipment and software will be purchased with a view to combining these into a coherent system. As the different organisations will sometimes be concentrating on different aspects of the EWS (e.g. this project focuses on monitoring/forecasting and communications, whereas PPCR or WFP may focus on responses and preparedness) it is important that this project first consults the information needed for preparedness and response activities, and works back to design appropriate information systems and forecasting/monitoring tools. Related activities through regional centres and activities such as FEWSNET (Famine and Early Warning System Network) will also be considered.

- Best practices and information will be shared between countries, especially where either the same sectoral EWS are planned and therefore use similar equipment and/or technologies, or nearby countries produce or monitor data and information that is relevant for other countries. The level of cooperation between countries will be dependent on political/institutional circumstances but the placement of new equipment may be optimised based on information from nearby countries e.g. upper air stations for regional climate modelling or weather radar. Best practises and successful applications of tailored climate information, sectoral impact models and decision support tools will also be shared to promote successful strategies and minimise mistakes.

B.3. 	Describe the socioeconomic benefits to be delivered by the Project at the national and local levels, including consideration of gender dimensions, and how these will support the achievement of global environment benefits. As a background information, read Mainstreaming Gender at the GEF.:

- The project is expected to deliver benefits at both the national and local levels. The installation of weather, upper air, radar and other observation and computer infrastructure will benefit the NHMS staff (through training and technological advancement). Other national institutions that will benefit from this endeavour will be Ministries of Agriculture, Water, Energy and Disaster Management, through strengthening of their computer databases, access to information and ability to communicate with other regions. One important benefit will be the improved coordination between government departments and the sharing of information, which can lead to improved products and services. It is then possible that these institutions can start marketing such information and products (satellite monitoring and climate forecast products in particular) to private entities that will pay for the services.

- At the local level early warnings and climate hazard mapping, disseminated correctly and acted on appropriately, can provide economic benefits through reducing losses of agricultural produce, infrastructure (roads and bridges) and disruption to peoples livelihoods. This has further knock-on effects on people’s health and wellbeing and thus affects communities and social structures. Communities will immediately benefit through warnings related to agriculture, coastal management, water and flood management, wildfires etc. This total population benefiting from these developments has the potential to grow hugely if warnings extend to a reasonable percentage of the total population e.g. through a mobile phone relay or similar system. Many of the beneficiaries will be women, especially within the agriculture sector where they often make up the majority of smallholder farmers, yet are most vulnerable to food insecurity. There may also be other benefits to developing the communication systems associated with early warnings - for instance radios can also be used for arranging medical evacuations.

- Perhaps the largest economic benefits are associated with improved transport planning, especially shipping which will take advantage of improved forecasts of winds and waves, and aviation which can take advantage of improved local forecasts. These and commercial agriculture likely represent some of the largest private clients for early warning services and tailored forecasts. Together with satellite imagery used for land-use planning and monitoring these can provide environmental benefits, including monitoring of illegal logging which has global consequences in terms of deforestation and the global carbon budget.

B.4. Indicate risks, including climate change risks that might prevent the project objectives from being achieved, and if possible, propose measures that address these risks

| Risk | Level | Mitigation |
| --- | --- | --- |
| Unavailability of requisite human resources and data | High | The issue of the unavailability of requisite human resources will be mitigated by recruitment of international consultants who will work closely with in-country counterparts and by targeted capacity building activities. Training activities of local personnel will also be part of all aspects of the work and the relevant institutions will be encouraged to expand the staff base if it is weak in particular areas. |
| Local IT and telecommunications infrastructure weak e.g. international bandwidth and local mobile telecommunications networks | Medium | Cost-effective solutions for each particular situation will be used e.g. satellite and/or radio communications. Where feasible automatic weather and hydrological stations reporting over the mobile telecoms network will be preferred. |
| Insufficient institutional support and political commitments | Medium | The proposed project is strongly supported by Governments and other key stakeholders and development partners. The project, in conjunction with UNDP, will therefore take advantage of this opportunity to seek substantial support from the Governments and forge strong partnership with other development partners. Direct linkages to existing and planned baseline development activities implemented by government, securing of the necessary co-financing, as well as local buy-in will also minimize this risk. It will also be important to establish buy in from all government departments early as the project will utilize data and information from a wide range of departments. |
| Work progresses in a compartmentalized fashion and there is little integration e.g. government departments refuse to share data and information | Medium | This risk is always present in a project such as this. By ensuring that capacity is built across a range of departments and implementing ‘quick win’ measures early (developing products based on internationally available data), these issues can be mitigated. |
| Non-compliance by primary proponents for the successful implementation of this project | Medium | Ensuring that the project is designed and implemented in a participatory and inclusive manner, following established UNDP procedures, will mitigate the risk. Since the activities correspond to the urgent needs as expressed by the primary proponents the risk of non-compliance should be reduced |
| Climate shock occurring during the design and implementation phase of the project | Low to medium | There may be some delays as more urgent priorities may need to be addressed by some of the stakeholders (e.g. NHMS or disaster management) but it is unlikely that this will derail the project. |

B.5. Identify key stakeholders involved in the project including the private sector, civil society organizations, local and indigenous communities, and their respective roles, as applicable:

| Stakeholder | Relevant roles |
| --- | --- |
| Regional |  |
| SADC Regional Meteorology Project (SAMPRO) | Not clear as yet – project is just starting but will likely invest in hard technologies e.g. weather stations and radars |
| Climate for Development in Africa Programme (ClimDev-Africa) | Promoting the use of climate information for development – potential partner for TA |
| African Monitoring of the Environment for Sustainable Development (AMESD) | Installing and promoting the use of satellite equipment and technology for environmental monitoring |
| Global Climate Observing System (GCOS) | Coordinating body for the climate observing system worldwide |
| Southern African Development Community Hydrological Cycle Observing System (SADC-HYCOS) | Coordinating the installation and use of hydrological monitoring equipment and information for water resource management |
| Global Facility for Disaster Reduction and Recovery (GFDRR) | Working mostly with disaster management, the programme also has a facility for advising on infrastructure development |
| Famine and early warning system network (FEWSNET) | Working across Africa to implement climate monitoring and forecasting for early warning in the food security sector |
| UNDP Bureau for Crisis Prevention and Recovery (UNDP-BCPR) and Environment and Energy Group | Working with disaster management, disaster and loss databases and climate risk assessments UNDP’s AAP programme is investing in both hard technology and the use of climate information for risk management |
| Zambia |  |
| Meteorology department | Run meteorological observation network and produce forecasts |
| Department of water affairs | Run hydrological observation network and associated supply infrastructure |
| Disaster mitigation and management unit | Coordinate disaster management activities under the office of the prime minister |
| Ministry of agriculture and livestock | Manage agricultural activities and food security assessments |
| Climate change secretariat | Successor to climate change facilitation unit (government coordination for climate change) |
| Zambia climate change network | NGO working with communities |
| Centre for Engineering, Energy and Environment | NGO working on adaptation |
| University of Zambia | Climate modelling and analysis |

B.6. Outline the coordination with other related initiatives:

- Climate for Development in Africa Programme (ClimDev-Africa) is a joint initiative of the Commission of the African Union (AUC), the African Development Bank (AfDB) and the United Nations Economic Commission for Africa (UNECA). ClimDev-Africa has received strong political endorsement from AU heads of state and government, African Ministers, several key stakeholders and the International Community. In general, the ClimDev-Africa programme supports Africa's response to climate variability and change by building regional, sub-regional and national policy capacity. It will improve the quality and availability of information and analysis to decision-makers.

- The African Monitoring of the Environment for Sustainable Development (AMESD) Project. The European Union funded project Preparation for the Use of MSG in Africa (PUMA) made available data and products from EUMETSAT’s latest satellites, promoting African National Meteorological and Hydrological Services to provide accurate weather forecasts, monitor extreme weather phenomena, and improve disaster management. The African Monitoring of the Environment for Sustainable Development (AMESD) initiative takes PUMA a stage further by significantly extending the use of remote sensing data to environmental and climate monitoring applications.

- The Global Climate Observing System (GCOS) is intended to be a long-term, user-driven operational system capable of providing the comprehensive observations required for: Monitoring the climate system; Detecting and attributing climate change; Assessing impacts of, and supporting adaptation to, climate variability and change; Application to national economic development; Research to improve understanding, modelling and prediction of the climate system. GCOS is a joint undertaking of the World Meteorological Organization (WMO), the Intergovernmental Oceanographic Commission (IOC) of the United Nations Educational Scientific and Cultural Organization (UNESCO), the United Nations Environment Programme (UNEP) and the International Council for Science (ICSU). It includes both in situ and remote sensing components, with its space based components coordinated by the Committee on Earth Observation Satellites (CEOS) and the Coordination Group for Meteorological Satellites (CGMS). GCOS is intended to meet the full range of national and international requirements for climate and climate-related observations.

- The Southern African Development Community Hydrological Cycle Observing System (SADC-HYCOS) is a regional component of the World Meterological Organisation (WMO) programme aimed at improving the basic observation activities, strengthening regional cooperation and promoting free exchange of data in the field of hydrology. The programme is guided by the World Hydrological Observing System (WHYCOS) International Advisory Group (WIAG). The aim is to ensure that participating countries, individually and collectively, attain the technical capability, effective management and equitable use of the freshwater resources of the sub-region and to establish a Water Resources Information System as an effective decision making tool

- The UNDP project, “Adaptation to the effects of drought and climate change in agro-ecological zones 1 and 2 in Zambia” (LDCF, $10.45m; implemented 2009-2013), seeks to address the Government’s insufficient use of EWS for the agricultural sector. It identifies two key weaknesses in the Government’s existing agricultural EWS programme:

- “outreach to farmers (including packaging the information in an accessible format)

- the links between the Ministry of Agriculture and the District authorities.”

- Within the Ministry of Agriculture, and at pilot sites, the project designs interventions to ensure that climate risk information is communicated effectively. A priority EWS intervention is for EWS to prevent the spread of livestock disease. The 2012 annual work plan for this project indicates that automatic weather stations will be installed at all 8 pilot sites throughout the year at a cost of $10,000.

- The PPCR programme in Zambia includes a climate information component to the project "Strengthening climate resilience in Zambia and the Barotse sub-basin." This totals $9.5m, including upgrading climate infrastructure ($4m) and developing EWS ($2.3m) (p. 74). The project "Private sector support to climate resilience" includes a climate information and dissemination network component, which includes activities to determine the feasibility of establishing a mobile phone platform in the private sector in Zambia ($0.3m) and to develop appropriate public-private sector partnerships to implement a mobile phone platform that provides market, technical and weather information to farmers ($4.5m).

- C. Describe the GEF agency’s comparative advantage to implement this project:

- The proposed project is aligned with UNDP’s comparative advantage, as articulated in the GEF matrix, in the area of capacity building, providing technical and policy support as well as expertise in project design and implementation. Additionally UNDP has close links with governments, as well as a high level of experience managing other LDCF projects in the region, in particular those with an early warning component. The figure below shows the value and sectoral focus of projects currently managed by UNDP which have a EWS component. UNDP is therefore already working with EWS in many countries and many sectors, strengthening its capability to coordinate and providing the flexibility to handle changing needs between countries. The country offices are supported by Regional Technical Advisors at UNDP offices in Pretoria, as well as by policy, adaptation, economics and climate modeling experts in New York, Cape Town and Bangkok.

- Within Zambia UNDP is closely involved with the Joint UN programme and PPCR programme, both of which include work on EWS. Close ties with the Disaster Management and Mitigation Unit (DMMU) within government further provide links to a broad set activities associated with EWS and disaster management, including the dissemination and uptake of warnings. The University of Zambia and Zambia Meteorological department have been partners within the Joint UN and PPCR programmes.

C.1. indicate the co-financing amount the GEF agency is bringing to the project:

- The total funding that UNDP is bringing to this project is $23,710,000. The details of these projects have been outlined above.

C.2. how does the project fit into the GEF agency’s programme (reflected in documents such as UNDAF, CAS, etc.)  and staff capacity in the country to follow up project implementation:

- Activities and results that will be developed under this project are also fully consistent with the UNDAF outcome 2.1 “Improved sustainable Natural Resource Utilization and food security”, 2.2 “Improved access to sustainable livelihoods opportunities in an innovative and competitive private sector”, and UNDAF outcome 2.3 "Improved access to sustainable basic infrastructure”.

- UNDP’s comparative advantage in implementing this project is underpinned by our energy and environment programme strategy which aims to mainstream environment and disaster prevention measures into national and local development policies, strategies and plans and our overarching role of capacity development.

- Public service reform and institutional building is one of UNDP’s flagship programming areas. The proposed capacity development activities in all components of the LDCF project will benefit from UNDP’s overarching and strategic role in this area, helping to ensure that related outcomes are sustainable in the long-term.

- There are other LDCF, SCCF and Adaptation Fund -financed projects within the region with similar objectives (see figure above) currently supported by UNDP, which means that there is substantial in-house technical expertise within UNDP that can be brought to bear to support the Government with the project as outlined above. UNDP country office operations are supported by regional advisory capacity based in the UNDP Regional Centre in Pretoria. UNDP has dedicated Regional Technical Advisers focusing on supporting adaptation programming and implementation in a range of technical areas relevant to this project including capacity development, coastal zone management, disaster management, infrastructure development, and ecosystem based adaptation. Our network of global Senior Technical Advisors provide additional technical oversight and leadership helping to ensure that programmes on the ground achieve maximum policy impact.

- UNDAF and CPD priorities for all countries will be outlined after conclusion of the PPG phase.

part iii: approval/endorsement by gef operational focal point(s) and GEF agency(ies)

A. Record of Endorsement of GEF Operational Focal Point (S) on Behalf of the Government(S):

| Name | Position | Ministry | Date (MM/DD/YYYY) |
| --- | --- | --- | --- |
| Dr K. Nkowani | Director | Ministry of Lands, natural resources and Environmental protection , Zambia | 04/19/2012 |

B. GEF Agency(ies) Certification

| This request has been prepared in accordance with GEF policies and procedures and meets the GEF criteria for project identification and preparation. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Agency Coordinator, Agency name | Signature | Date | Project Contact Person | Telephone | Email Address |
| Yannick Glemarec Executive Coordinator UNDP/GEF |  | May 8, 2012 | Mark Tadross Technical Advisor Gr-LECRDS | +27 21 6502884 | Mark.tadross@undp.org |

http://hdr.undp.org/en/reports/global/hdr2011/

Di Baldassarre, G., A. Montanari, H. Lins, D. Koutsoyiannis, L. Brandimarte, and G. Blöschl (2010), Flood fatalities in Africa: From diagnosis to mitigation, Geophys. Res. Lett., 37, L22402, doi:10.1029/2010GL045467

IPCC, 2012:Managing the Risks of Extreme Events and Disasters to Advance Climate Change Adaptation.A Special Report of Working Groups I and II of the Intergovernmental Panel on Climate Change [Field, C.B., V. Barros, T.F. Stocker, D. Qin, D.J. Dokken, K.L. Ebi, M.D. Mastrandrea, K.J. Mach, G.-K. Plattner, S.K. Allen, M. Tignor, and P.M. Midgley (eds.)]. Cambridge University Press, Cambridge, UK, and New York, NY, USA, 582 pp

Knutson1 T, Mcbride J, Chan J, Emanuel K, Holland G, Landsea C, Held I, Kossin J, K Srivastava and M Sugi (2010). Tropical cyclones and climate change. Nature Geoscience. doi: 10.1038/ngeo779.

World Bank (2010). Natural hazards, Unnatural disasters: Effective prevention through an economic lens. World Bank and United Nations. 231 pp.

http://www.amesd.org/index.php?start=25

http://www.un.org/apps/news/story.asp?NewsID=31193&Cr=weather&Cr1

http://www.wmo.int/pages/prog/gcos/index.php

see WMO Global Framework for Climate Services

See GFDRR WCIDS: http://www.gfdrr.org/gfdrr/WCIDS

http://www.dmi.dk/dmi/en/index/klima/danish_climate_centre/developing_countries.htm

http://www.worldresourcesreport.org/responses/ranet-project-climate-information-collection-zambia

http://www.scribd.com/Zambian-Economist/d/72406609-2012-Budget-Address-by-Hon-Chikwanda

UNDP LDCF PIF, “Adaptation to the effects of drought” p. 7

http://www.dmi.dk/dmi/en/print/index/klima/danish_climate_centre/developing_countries.htm

http://www.servir.net/africa/index.php?option=com_frontpage&Itemid=1

http://www.rockefellerfoundation.org/what-we-do/current-work/developing-climate-change-resilience/grants-grantees/african-agriculture-climate-change

http://www.fews.net/Pages/default.aspx